## Sheet1
Project | Triangle
| Estimates | Actual
Lines of Code | 200 | 249
Time(in minutes) | 360 | 605
Errors | 30 | 15
| Current Report |  |  |  | Grand totals
| Estimates | Actuals | rel error |  | Estimates | Actuals | total rel error
Lines of Code | 200 | 249 | 24.5% | Lines of Code | 200 | 249 | 24.5%
Time | 360 | 605 | 68.06% | Time | 360 | 605 | 68.06%
Errors | 30 | 15 | 50% | Errors | 30 | 15 | 50%
Time Log
date | start | stop | elapsed | reason stopped | phase | loc | reused | modified | deleted
2013-09-03 | 11:00 | 11:30 | 30 | class | requirements analysis | 0 | 0 | 0 | 0
2013-09-05 | 13:00 | 14:00 | 60 | logic block | requirements analysis | 0
2013-09-05 | 15:00 | 15:10 | 10 | logic clarification | requirements analysis | 10
2013-09-10 | 8:00 | 9:00 | 60 | work | design | 50 |  | 10
2013-09-10 | 18:00 | 19:00 | 60 | meeting | implementation | 26
2013-09-10 | 20:00 | 20:30 | 30 | distracted | implementation | 0 | 30 | 20 | 20
2013-09-10 | 22:00 | 23:30 | 90 | distracted | implementation | 40 | 8 | 20 | 30
2013-09-11 | 20:30 | 21:00 | 30 | stop | implementation | 0 | 0 | 4 | 0
2013-09-12 | 10:00 | 12:00 | 120 | break | implementation | 30 |  | 10 | 4
2013-09-12 | 12:05 | 13:00 | 55 | class | testing and documentation | 20 | 3 |  | 5
2013-09-12 | 16:00 | 17:00 | 60 | done | testing and documentation | 20 |  | 10 | 3
|  |  | 605 |  |  | 196 | 41 | 74 | 62
[8 empty] | Grand Total | 249
Error Key |  | Error log
100 Semantic |  | date | error | type | discovered | injected | corrected
105 Missing semi colon |  | 2013-09-10 | 1 | 105 | 20:15 | implementation | 20:15
110 not enough parameters |  | 2013-09-10 | 2 | 105 | 20:17 | implementation | 20:18
115 missing parenthesis or brace |  | 2013-09-10 | 3 | 115 | 20:20 | implementation | 20:23
120 Markdown Error |  | 2013-09-10 | 4 | 305 | 20:25 | implementation | 20:40
125 resource not found |  | 2013-09-11 | 5 | 105 | 20:30 | implementation | 20:31
130 Doxygen error |  | 2013-09-11 | 6 | 105 | 20:32 | implementation | 20:33
|  | 2013-09-11 | 7 | 315 | 20:35 | implementation | 20:37
|  | 2013-09-12 | 8 | 110 | 12:00 | implementation | 12:05
|  | 2013-09-12 | 9 | 115 | 12:05 | implementation | 12:06
200 Runtime |  | 2013-09-12 | 10 | 210 | 12:15 | implementation | 12:16
205 out of scope |  | 2013-09-12 | 11 | 220 | 12:45 | implementation | 1:00
210 loop error |  | 2013-09-12 | 12 | 120 | 16:00 | testing and documenting | 16:05
215 undefined variables |  | 2013-09-12 | 13 | 130 | 16:15 | testing and documenting | 16:20
220 no-output |  | 2013-09-12 | 14 | 125 | 16:30 | testing and documenting | 16:30
225 exception error |  | 2013-09-12 | 15 | 120 | 16:45 | testing and documenting | 16:50
300 Logic Error
305 design issue
310 logic gap
315 missing input